EPROM

Competency Management System

EXECUTIVE SUMMARY & GO-LIVE PLAN

Status • Benefits • Obstacles • Roadmap (from 1 July 2026) Cost

Prepared by: Training Capacity Building Committee

Group 12:

| - Eng Ahmed EL kilany | - Eng Mohamed Elyamani |
| --- | --- |
| - Eng Ali Ahmed | - Eng Tariq Salama |

# 0. At a Glance

The EPROM Competency Management System (CMS) is a working web application that digitizes the full employee skill cycle — defining required skills per role, assessing each employee, and auto-generating training plans and career paths. The software is built and functional. What remains is a controlled deployment to put it in front of EPROM staff for internal use.

| Item | Status |
| --- | --- |
| Software build (all modules) | Complete and functional |
| Readiness for internal go-live | ~95% — pending deployment setup |
| Earliest internal go-live (Cloud path) | Late July 2026 |
| Earliest internal go-live (On-Premises path) | Late September 2026 |
| One-time setup cost (Cloud path) | ~EGP 0–20,000 |
| Annual running cost (Cloud, 4,000 users) | ~EGP 42,000–84,000 |
| Annual saving vs. current manual process | ~EGP 6 million |

# 1. What Has Been Done

The full application has been designed, built, and is operating against a live cloud database. Delivered work:

## 1.1 Functional Modules Built

| Module | What It Does |
| --- | --- |
| Skills Catalog | All technical & behavioral competencies on a 1–5 proficiency scale |
| Job Profiles | Maps each org level (FR → GM) to the skills and level it requires |
| 360° Assessments | Self (10%) + Peer (30%) + Manager (60%) weighted scoring |
| Technical Assessments | Written exams, managerial interviews, practical demonstrations |
| Evidence Portal | Employees submit work records; managers approve and score |
| Skill Gap Reports | Instant gap of each employee vs. their required level |
| Individual Training Plans (ITP) | Auto-generated from gaps, linked to courses |
| Career Path Planner | Readiness to advance to the next org level |
| Assessment Scheduling | Defines how/when each skill is re-assessed |
| CEO & Manager Dashboards | Real-time org-wide and team analytics |
| Bulk Employee Import | Onboard hundreds of staff via Excel in minutes |

## 1.2 Engineering & Infrastructure Completed

•  Full React + TypeScript front-end, responsive for desktop and tablet.

•  Firebase Firestore database live, with role-based access (Admin / CEO / Manager / Employee).

•  Firestore security rules generated from a template and ready to deploy.

•  Organization hierarchy seeded as a full company org chart (bilingual EN/AR), HQ structure in place.

•  Department / section data-visibility scoping enforced (staff see only their own scope; Admin/CEO see all).

•  Bulk Excel import pipeline tested for mass employee onboarding.

•  Production deployment guide written for both Cloud and self-hosted (on-premise) paths.

# 2. What It Achieves When Live

Once in internal use, the system replaces a slow, manual, spreadsheet-driven process with a real-time platform. Concrete outcomes:

•  One source of truth — every employee's required vs. actual skill level, visible instantly.

•  Automatic skill-gap analysis across all employees — no manual consolidation.

•  Auto-generated Individual Training Plans (ITP) per employee, linked to specific courses.

•  Departmental Training Needs Analysis (TNA) produced in minutes instead of weeks.

•  Career-path & succession readiness scoring (Ready Now / 1–2 yrs / 3–5 yrs / Not Ready).

•  Audit-ready competency records supporting ISO 9001 (Clause 7.2), ISO 55001, and OPITO compliance.

•  Real-time CEO and manager dashboards for data-driven L&D and promotion decisions.

•  A direct pipeline from each identified skill gap to a Training Center enrollment.

## 2.1  Quantified Impact (4,000 employees)

| Measure | Today (Manual) | With CMS |
| --- | --- | --- |
| Annual competency-admin cost | ~EGP 6.19 million | ~EGP 0.18 million |
| Skill-gap analysis | 1 hr × 4,000 staff | Instant / automated |
| Org-wide TNA report | Weeks of analyst work | ~6 minutes |
| ITP creation & distribution | 1.5 hr × 4,000 staff | Auto-generated |
| NET BENEFIT | — | ~EGP 6 million / year saved |

Payback period against the one-time development cost is under two weeks of operation.

# 3. Obstacles & How to Manage Them

The remaining items are deployment and adoption tasks, not software defects. Each has a clear owner and mitigation.

## 3.1  Technical Blockers (must clear before go-live)

| Obstacle | Why It Matters | How to Manage | Owner / Effort |
| --- | --- | --- | --- |
| Authorized domain | Logins are rejected from an unknown domain | Add cms.eprom.com.eg to the authorized list | Owner — 5 min |
| HTTPS / SSL certificate | Login requires a secure connection | Free Let's Encrypt or company CA certificate | IT — 1–2 hrs |
| Production config file | App can't reach the database without it | Create .env.production from documented keys | Owner — 15 min |
| Firewall outbound (Cloud path) | App must reach the cloud database | Allow outbound HTTPS to the database endpoints | IT — 1 hr |

## 3.2  Hardening Tasks (week 1, non-blocking)

•  Idle session auto-logout (30-minute timeout) — ~4 hrs developer.

•  Network-outage error banner so users aren't confused on dropouts — ~3 hrs developer.

•  HTTP security headers (anti-clickjacking, CSP) on the web server — ~2 hrs IT.

## 3.3  Organizational Obstacles

| Obstacle | How to Manage |
| --- | --- |
| Change management — 4,000 staff moving off spreadsheets | Department-by-department rollout; short manager briefings; start with one pilot dept |
| Data quality — existing skill data is messy | Clean & standardize once, then mass-import via the Excel template |
| User adoption & trust in the scores | Transparent scoring rules; managers validate the first cycle before publishing |
| Single-owner dependency | Document deployment & admin steps; train one HR admin as backup champion |
| IT coordination | Use the written deployment guide; pre-agree server/network tasks with IT |

## 3.4 Technical Debt (after launch, not blocking)

•  Move heavy calculations (TNA, career path) server-side for scale beyond 200 concurrent users.

•  Stronger role security via Firebase Auth custom claims (Cloud path).

•  Loading skeletons and subordinate-lookup speed-ups for polish at scale.

# 4. Go-Live Roadmap — from 1 July 2026

Two paths to internal go-live. The Cloud path reuses the current build and is live within weeks. The On-Premise path keeps all data on EPROM servers but requires a back-end rewrite first, pushing go-live later. Both can start on 1 July 2026.

## 4.1  Option A — Cloud (Firebase) — RECOMMENDED for now

Uses the system exactly as built. Fastest, lowest cost, no hardware. Data resides on Google Cloud (GDPR-compliant data centers).

| Phase | Dates (2026) | Activities |
| --- | --- | --- |
| 0 — Setup & blockers | 1 Jul – 10 Jul | Domain, SSL, production config, firewall, security headers |
| 1 — Pilot | 13 Jul – 22 Jul | Smoke test with 5–10 users (HR + IT + one dept); fix feedback |
| 2 — Data load | 23 Jul – 30 Jul | Load skills, job profiles; bulk-import employees; assign profiles |
| GO-LIVE (internal) | 31 Jul 2026 | Open to pilot department; first assessment cycle begins |
| 3 — Full rollout | Aug – Sep | Department-by-department onboarding of all 4,000 staff |
| 4 — First reports | Sep 2026 | First org-wide TNA, ITPs, and board competency report |

Cloud path total time to internal go-live: ~4 weeks. Effort: ~20–30 IT hours + ~30–40 developer hours.

## 4.2  Option B — On-Premise (all data on EPROM servers)

Keeps 100% of data inside the company. Requires rewriting the back-end from Firebase to PostgreSQL + a local login server, plus server hardware. Choose this only if corporate data policy mandates it.

| Phase | Dates (2026) | Activities |
| --- | --- | --- |
| 0 — IT provisioning | 1 Jul – 14 Jul | Server, OS, network, install Nginx / Node / PostgreSQL |
| 1 — Back-end rewrite | 1 Jul – 22 Aug | Rebuild data layer on PostgreSQL + local authentication (8 wks) |
| 2 — Deploy & migrate | 25 Aug – 5 Sep | Deploy app, load schema, migrate data, enable HTTPS |
| 3 — Testing & sign-off | 8 Sep – 19 Sep | Security checks, backups, pilot test |
| GO-LIVE (internal) | 25 Sep 2026 | Open to staff; cloud build decommissioned |
| 4 — Full rollout | Oct 2026 | Onboard all 4,000 staff; first reports |

On-Premise path total time to internal go-live: ~12 weeks (driven by the back-end rewrite).

## 4.3  Recommended Sequence

•  Go live on the Cloud path on 31 July 2026 to capture savings immediately.

•  Run internally on Cloud while evaluating whether data policy truly requires on-premise.

•  If required, execute the On-Premise migration as a Phase-2 project later in 2026 — with zero downtime to users.

# 5. Cost Estimation

## 5.1  Cloud Path (Recommended)

| Item | Type | Estimated Cost |
| --- | --- | --- |
| Domain (subdomain of eprom.com.eg) | One-time | EGP 0 (already owned) |
| SSL certificate (Let's Encrypt) | One-time | EGP 0 |
| Setup / config labor | One-time | Internal IT + developer hours |
| Cloud database & hosting (4,000 users) | Annual | EGP 30,000–72,000 |
| Maintenance & improvements (AI tooling) | Annual | ~EGP 12,000 |
| TOTAL annual running cost | Annual | ~EGP 42,000–84,000 |

≈ EGP 3,500–7,000 per month all-in — under 0.2% of the ~EGP 6 million/year it saves.

## 5.2  On-Premise Path

| Item | Type | Estimated Cost (EGP) |
| --- | --- | --- |
| Server hardware (app + DB + backup, UPS, network) | One-time capex | 810,000 – 1,250,000 |
| Back-end rewrite (Firebase → PostgreSQL) | One-time dev | 150,000 – 250,000 |
| Software (PostgreSQL, Keycloak, Nginx — open source) | Licensing | 0 |
| IT administration (1 FTE, server upkeep) | Annual | 180,000 – 240,000 |
| Electricity + warranty / support | Annual | 58,000 – 110,000 |
| TOTAL 3-year cost of ownership | 3-year | ~1,674,000 – 2,550,000 |

On-premise costs roughly 9–14× the cloud path over three years. A lower-capex alternative is leasing colocation rack space (~EGP 15,000–30,000/month) instead of buying hardware.

## 5.3  Cost vs. Commercial Alternatives

| Solution | Annual Infrastructure | Licensing / Implementation |
| --- | --- | --- |
| EPROM CMS (Cloud) | EGP 42,000–84,000 | Negligible (in-house) |
| SAP SuccessFactors | $50,000–200,000 | $500,000+ implementation |
| Oracle HCM Cloud | $40,000–150,000 | $300,000+ setup |
| Generic local HR SaaS | EGP 30,000–80,000 | No competency module |

The EPROM CMS delivers enterprise-grade competency management at under 0.5% of the cost of SAP or Oracle.

# 6. Recommendation

•  Approve internal go-live on the Cloud path with a target date of 31 July 2026.

•  Assign one HR manager as CMS Administrator (data owner and internal champion).

•  Start with a single pilot department, then roll out company-wide through August–September.

•  Defer the on-premises decision: revisit only if corporate data policy mandates it, and run it as a no-downtime Phase-2 migration.

Bottom line: the system is built and the savings are real. The Cloud path turns it into live internal value within four weeks of starting on 1 July 2026, at a running cost that is a rounding error against the EGP 6 million it saves each year.